## Sheet1
CankayaUniversity/ceng-407-408-2023-2024-Binel
Begin Date 23/10/2023 |  | 2023-10-02 | 2023-10-13 | 2023-10-16 | 2023-10-27 | 2023-11-03 | 2023-11-06 | 2023-11-13 | 2023-11-20 | 2023-11-27 | 2023-12-08 | 2023-12-15 | 2023-12-22 | 2023-12-29 | 2024-01-05 | 2024-01-12
Action Steps (What Will Be Done) | Status | Week1 | Week2 | Week3 | Week4 | Week5 | Week6 | Week7 | Week8 | Week9 | Week10 | Week11 | Week12 | Week13 | Week14 | Week15
Project Proposal Form | Done | bar: 2023-10-02 to 2023-10-13
Team Setup | Done | bar: 2023-10-02
Project Selection Form | Done | bar: 2023-10-02
GitHub Repository | Done | bar: 2023-10-13 to 2023-10-16
Project Work Plan | In Progress | bar: 2023-10-16 to 2023-10-27
Literature Review | In Progress | bar: 2023-10-16 to 2023-11-03
Software Requirements Specification | In Progress | bar: 2023-11-06 to 2023-11-27
Project Webpage | In Progress | bar: 2023-11-20 to 2023-12-08
Software Design Description | In Progress | bar: 2023-12-08 to 2023-12-22
Project Report / Project Tracking Form | In Progress | bar: 2023-12-29 to 2024-01-05
Presentation | In Progress | bar: 2024-01-12